## Sheet1
Phase | Task # | Detailed Task Description (Point-wise) | Rationale & Key Considerations | Comments
Phase 1: Foundational Feature Engineering | 1 | Create Client Lifecycle Features • age_at_first_policy = YEAR(register_date) - YEAR(birth_dt) • Temporal Features: month, quarter, and dayofweek from register_date | Goal: Provide temporal and demographic context — key drivers of purchasing patterns.
| 2 | Create Client Financial Profile Features • 1. wealth_to_premium_ratio = wc_total_assets / (monthly_premium_amount * 12) • 2. policy_value_to_assets_ratio = face_amt / wc_total_assets • 3. Asset Mix Ratios: For each X in [stocks, bonds, mutual_funds, annuity, deposits], compute wc_assetmix_X / wc_total_assets | Goal: Move from absolute values to ratios, better reflecting client financial behavior and capacity. | 1. A lot of 'null's for many clients are present to use the 1st
| 3 | Re-train and Evaluate (Checkpoint 1) • 1. Run Pipeline: Use enriched dataset (Tasks 3–4). • 2. Log & Compare: Compare new weightedF1 vs. baseline. • 3. Document: Expected F1 improvement. | Goal: Quantify ROI of the first feature batch before deeper modeling.
Phase 2: Advanced Feature Engineering | 4 | Create Agent-Centric Features • 1.agent_tenure_at_sale = datediff(register_date, esf_hire)/365.25 | Goal: Agents influence cross-sell success; these features quantify their experience and context. | 1. can't compute agent tenure due to lack of agent table
| 5 | Create “Propensity” Aggregate Features • 1. Build cross_sell_history with ( first_prod_code , second_prod_code , agt_no , branchoffice_code ). • 2. Aggregates: – Product Propensity: count of second_prod_code per first_prod_code. – Agent Propensity: count of second_prod_code per (agt_no, first_prod_code). • 3. Join Back: Merge aggregates to main DF (train/test), fill NaNs with 0. | Goal: Capture behavioral “wisdom of the crowd.” Must be computed only on training data to prevent leakage. | 2. No agent table information
| 6 | Re-train and Evaluate (Checkpoint 2) • 1. Run Pipeline: Train with all features from Phases 1 & 2. • 2. Log & Compare: Expect weightedF1 = 0.75–0.78. | Goal: Validate lift from agent + behavioral features.
Phase 3: Model Optimization & Tuning | 7 | Upgrade GBT & Handle Class Imbalance • 1. Switch: Use synapseml.lightgbm.LightGBMClassifier . • 2. Handle Imbalance: Set setIsUnbalance(True) or add a weightCol using inverse class frequency. | Goal: Leverage LightGBM for better performance and explicitly balance underrepresented classes.
| 8 | Systematic Hyperparameter Tuning • 1. Search Space: Define Hyperopt search for learning_rate , numLeaves , maxDepth , subsample , colsampleBytree . • 2. Objective: Train model with params and return {'loss': -weighted_f1} . • 3. Run: Use SparkTrials() with max_evals=50 and tpe.suggest . | Goal: Replace manual tuning with distributed Bayesian optimization to maximize F1.
| 9 | Re-train and Evaluate (Checkpoint 3) • 1. Train Final Model: Use best parameters from Hyperopt. • 2. Evaluate: Compute weightedF1 on held-out test set (~0.79–0.82+). | Goal: Confirm final model performance on unseen data.
Phase 4 & 5: Finalization | 10 | Feature Importance & Interpretation • 1. Extract: model.getFeatureImportances() for LightGBM. • 2. Use SHAP for deep interpretability. | Goal: Build explainability and stakeholder trust.